## Cost and Budget Tracking
Category | Item Description | Supplier | Quantity | Unit Cost | Total Cost | Budgeted Amount | Variance | Payment Status | Notes
design | Architectural Design Fees | Stephenson-Edwards Studio | 1 | 25000 | 25000 | 28000 | 3000 | paid | Final burrow layout approved Apr 5
design | Interior Design Services | Tokkia Design Partners | 1 | 18000 | 18000 | 20000 | 2000 | paid | Terrazzo & lime-wash specs Apr 10
engineering & consulting | Structural Engineering | EngStruct London | 1 | 8000 | 8000 | 9000 | 1000 | pending | Low-ceiling analysis complete Apr 12
engineering & consulting | MEP Engineering Plans | MechEng UK | 1 | 6500 | 6500 | 7000 | 500 | paid | Ventilation for matcha stations Apr 15
permits & approvals | Planning Application | Camden Council | 1 | 4000 | 4000 | 4500 | 500 | paid | Covent Garden heritage ok Apr 8
permits & approvals | Building Regs Approval | LABC London | 1 | 2500 | 2500 | 2800 | 300 | paid | Food-safe compliance Apr 18
permits & approvals | Site Surveys | SurveyPro Ltd | 1 | 3000 | 3000 | 3200 | 200 | paid | Monmouth St measurements Apr 3
design | 3D Renderings | RenderHub Studio | 1 | 5000 | 5000 | 5500 | 500 | pending | Bunny-themed visuals delivered Apr 20
engineering & consulting | Landscape Consultant | GreenSpace Assoc | 1 | 2000 | 2000 | 2200 | 200 | paid | Street-facing tweaks Apr 7
design | Acoustic Design | SoundEng Ltd | 1 | 3500 | 3500 | 3800 | 300 | pending | Calming ambiance plans Apr 22
engineering & consulting | Sustainability Audit | EcoBuild Partners | 1 | 4000 | 4000 | 4200 | 200 | paid | Energy standards met Apr 14
design | Quantity Surveyor | QS Experts | 1 | 7000 | 7000 | 7500 | 500 | paid | Initial cost plan Apr 9
design | Project Management | PMG London | 1 | 12000 | 12000 | 13000 | 1000 | partial | Phase oversight Apr 1-30
design | Lighting Design | Lumina Studio | 1 | 4500 | 4500 | 4800 | 300 | pending | Earthy matcha glow Apr 25
fixtures & equipment | Fixture Prototyping | BronzeCraft | 1 | 6000 | 6000 | 6500 | 500 | paid | Teaware integration Apr 16
engineering & consulting | Heritage Consultant | HeritageUK | 1 | 3500 | 3500 | 3700 | 200 | paid | Seven Dials compliance Apr 11
engineering & consulting | Fire Safety Eng | FireSafe Pro | 1 | 4000 | 4000 | 4200 | 200 | pending | Compact space cert Apr 28
engineering & consulting | Accessibility Audit | AccessCheck Ltd | 1 | 2500 | 2500 | 2700 | 200 | paid | Burrow ramps planned Apr 19
design | Signage & Graphics | SignArt London | 1 | 3000 | 3000 | 3200 | 200 | paid | Timber entrance Apr 6
design | Design Revisions | Internal Reserve | 1 | 10800 | 10800 | 12000 | 1200 | pending | Minor earthy texture changes Apr 27
materials | Terrazzo Samples | TerraFloor Supplies | 10 | 450 | 4500 | 5000 | 500 | paid | Matcha station prototypes Apr 13
materials | Lime Wash Paint | EcoPaints UK | 50 | 120 | 6000 | 6500 | 500 | partial | Wall finish trials Apr 21
fixtures & equipment | Survey Tools Rental | ToolHire London | 15 | 80 | 1200 | 1500 | 300 | paid | Laser measures Apr 4
fixtures & equipment | CAD Software License | Autodesk UK | 1 | 2800 | 2800 | 3000 | 200 | paid | Monthly sub Apr 1
fixtures & equipment | Site Visits | Team Travel | 8 | 150 | 1200 | 1500 | 300 | paid | Covent Garden trips Apr 2-29
fixtures & equipment | Blueprints & Plans | PrintPro London | 200 | 15 | 3000 | 3200 | 200 | paid | A1 sets Apr 17
fixtures & equipment | Courier Deliveries | DHL UK | 12 | 45 | 540 | 600 | 60 | paid | Docs to council Apr 10-26
[5 empty] | 154040 | 169100 | 15060 | 19 Paid / 27 Total | Under Budget by £15060

## Contractor and Labor Management
Contractor | Role | Task | Start Date | End Date | Contract Value | Amount Paid | Remaining Balance | Status | Required Materials | Key Delivery Date | Delivery Status
Stephenson Edwards Studio | Architect | Architectural Design Fees | 2026-04-01 | 2026-04-05 | 25000 | 25000 | 0 | paid | General Materials
Tokkia Design Partners | Interior Designer | Interior Design Services | 2026-04-06 | 2026-04-10 | 18000 | 18000 | 0 | paid | General Materials
EngStruct London | Structural Engineer | Structural Engineering | 2026-04-08 | 2026-04-12 | 8000 | 0 | 8000 | pending | General Materials
MechEng UK | MEP Engineer | MEP Engineering Plans | 2026-04-06 | 2026-04-10 | 6500 | 6500 | 0 | paid | General Materials
Camden Council | Planning Authority | Planning Application | 2026-04-08 | 2026-04-12 | 4000 | 4000 | 0 | paid | General Materials
LABC London | Building Control | Building Regs Approval | 2026-04-10 | 2026-04-15 | 2500 | 2500 | 0 | paid | General Materials
SurveyPro Ltd | Surveyor | Site Surveys | 2026-04-01 | 2026-04-08 | 3000 | 3000 | 0 | paid | General Materials
RenderHub Studio | Renderer | 3D Renderings | 2026-04-15 | 2026-04-20 | 5000 | 0 | 5000 | pending | General Materials
GreenSpace Assoc | Landscape Consultant | Landscape Consultancy | 2026-04-01 | 2026-04-07 | 2000 | 2000 | 0 | paid | Landscape Plant Samples | 2026-02-24 | delivered
SoundEng Ltd | Acoustic Consultant | Acoustic Design | 2026-04-18 | 2026-04-22 | 3500 | 0 | 3500 | pending | General Materials
EcoBuild Partners | Sustainability Consultant | Sustainability Audit | 2026-04-10 | 2026-04-14 | 4000 | 4000 | 0 | paid | General Materials
QS Experts | Quantity Surveyor | Quantity Surveyor Services | 2026-04-05 | 2026-04-09 | 7000 | 7000 | 0 | paid | General Materials
PMG London | Project Manager | Project Management | 2026-04-01 | 2026-04-30 | 12000 | 6000 | 6000 | partial | General Materials
Lumina Studio | Lighting Designer | Lighting Design | 2026-04-20 | 2026-04-25 | 4500 | 0 | 4500 | pending | Pendant Lamps, Matcha Counter Lighting |  | pending
BronzeCraft | Fabricator | Fixture Prototyping | 2026-04-10 | 2026-04-16 | 6000 | 6000 | 0 | paid | Teaware Fixture Prototypes | 2026-02-16 | delivered
HeritageUK | Heritage Consultant | Heritage Review | 2026-04-05 | 2026-04-28 | 3500 | 3500 | 0 | paid | Heritage Compliance Files |  | delivered
FireSafe Pro | Fire Safety Engineer | Fire Safety Engineering | 2026-04-20 | 2026-04-28 | 4000 | 0 | 4000 | pending | Safety Certificates | 2026-02-28 | pending
AccessCheck Ltd | Accessibility Consultant | Accessibility Audit | 2026-04-10 | 2026-04-19 | 2500 | 2500 | 0 | paid | Accessibility Audit Reports |  | delivered
SignArt London | Signage Designer | Signage & Graphics | 2026-04-02 | 2026-04-06 | 3000 | 3000 | 0 | paid | Custom Signage | 2026-02-18 | delivered
Internal Reserve | Design Revisions | Design Adjustments | 2026-04-20 | 2026-04-27 | 10800 | 0 | 10800 | pending | General Materials

## Procurement and Deliveries
Item | Supplier | Order Date | Expected Delivery | Received Date | Quantity | Status | Invoice # | Notes
Bamboo Floor Planks | Eco Build Ltd | 2026-02-10 | 2026-02-20 | 2026-02-21 | 200 | delivered (late) | INV 1025
Terrazzo Tiles | TerraFloor Supplies | 2026-02-15 | 2026-02-25 | 2026-02-25 | 300 | delivered | INV 1032
Lime-Wash Paint | EcoPaints UK | 2026-02-12 | 2026-02-22 | 2026-02-21 | 50 | delivered | INV 1029
Pendant Lamps | Luminaa Studio | 2026-02-14 | 2026-02-27 |  | 20 | pending | INV 1040
Custom Signage | SignArt London | 2026-02-08 | 2026-02-18 | 2026-02-17 | 10 | delivered | INV 1019
Teaware Fixture Prototypes | BronzeCraft | 2026-02-10 | 2026-02-16 | 2026-02-16 | 5 | delivered | INV 1020
Matcha Counter Lighting | Luminaa Studio | 2026-02-18 | 2026-02-25 |  | 8 | pending | INV 1042
Terrazzo Sample Set | TerraFloora Supplies | 2026-02-11 | 2026-02-20 | 2026-02-19 | 10 | delivered | INV 1030
Heritage Compliance Files | HeritageUK | 2026-02-10 | 2026-02-15 | 2026-02-15 | 3 | delivered | INV 1028
Safety Certificates | FireSafe Pro | 2026-02-14 | 2026-02-28 |  | 1 | pending | INV 1044
Accessibility Audit Reports | AccessCheck Ltd | 2026-02-12 | 2026-02-19 | 2026-02-19 | 2 | delivered | INV 1033
Landscape Plant Samples | GreenSpace Assoc | 2026-02-14 | 2026-02-24 | 2026-02-24 | 50 | delivered | INV 1041
CAD Software License | Autodesk UK | 2026-02-01 | 2026-02-01 | 2026-02-01 | 1 | delivered | INV 1005
Blueprint Sets | PrintPro London | 2026-02-10 | 2026-02-17 | 2026-02-17 | 200 | delivered | INV 1027
Courier Deliveries | DHL UK | 2026-02-13 | 2026-02-26 |  | 15 | pending | INV 1043
Site Survey Tools Rental | ToolHire London | 2026-02-04 | 2026-02-10 | 2026-02-09 | 15 | delivered | INV 1012
Procurement Summary |  |  | Label
Total Items Ordered | 21 |  | Delivered (On Time) | 11
Pending Deliveries | 4 |  | Pending | 4
Delivered (Late) | 1 |  | Delivered (Late) | 1
Percent Delivered (On Time) | 68.75%

## Dashboard
TOKKIA MATCHA HOUSE - PROJECT DASHBOARD
Total Budget | 338200
Total Spent | 308080
Remaining Budget | 30120
Percentage of Budget Used | 91.09%
Over Budget Items | 0
Paid Items | 19
Top 5 Expense Categories
Design | 88800 | 28.82%
Engineering & Consulting | 30500 | 9.9%
Materials | 10500 | 3.408%
Permits & Approvals | 9500 | 3.084%
Fixtures & Equipment | 14740 | 4.784%